## Altimeter
Project Dashboard -Altimeter Board
M. Zaeem ¦ Electronics & Embedded Systems Engineer ¦ BSc Electrical Engineering ¦ MSc Autonomous Systems
1. Project Basic Information
Project Name: | Altimeter Board (To record altitude and acceleration)
Client Name: | Chris Flanigan
Start Date: | 2025-09-29 |  | Expected End Date: | 2025-10-31
Pricing Model: | Fixed Price | Hourly Rate
Hourly Rate Per Hour ($): | 15 |  | Total Project Budget: |  | 1500
Payment by Milestone:
2. Project Requirements
3. Project Milestones
Milestone 1- (Hardware selection, component validation, preliminary system design) | Task Requirements |  | Hours Spent | Description | Status
| Define system architecture and finalize MCU selection |  | 6 | System Architecture & Component Selection | Completed
| Identify and validate sensors |  | 2 |  | Completed
| Feasibility analysis of components and connectivity |  | 2 |  | Completed
| Order pre-assembled modules |  | 1 |  | Completed
| Develop basic Arduino firmware for sensor interfacing. |  | 5 |  | Completed
| Milestone 1 Hours : |  | 16
Milestone 2- (Sensor integration, firmware development, ground station interface) | Task Requirements |  | Hours Spent | Description | Status
| Integrate sensors with MCU and implement non-volatile memory logging |  | 26 | Data Acquisition & Storage Implementation | Completed
| Develop Python-based ground station interface for data retrieval via BLE |  | 16 |  | Completed
| Perform functional verification of sensor readout and data logging |  | 4 |  | In Progress
| Benchmark and validate data integrity and transfer reliability |  | 4 |  | Completed
| Implement X-Y plotting of data using Graph. |  | 4 |  | Completed
| Milestone 2 Hours : |  | 54
Milestone 3- (PCB design, fabrication prep, final delivery) | Task Requirements |  | Hours Spent | Description | Status
| Making detailed schematic diagram (Altium) |  | 16 | PCB Design & BOM | Completed
| PCB layout (Altium) |  |  |  | Pending
| Generate Gerber files and assembly documentation |  |  |  | Pending
| Ordering PCBS |  |  |  | Pending
| Uploading Firmware and Bootloader |  |  |  | Pending
| Testing and Pakaging |  |  |  | Pending
| Shipping to Client |  |  |  | Pending
| Milestone 3 Hours : |  | 16
4. Key Deliverables |  | Additional Requirements | Project End Goal and Approval Criteria
Sensor Selection |  | Hardware | All hardware components functioning to specification Software meets All requirements with no critical bugs Client signs off on final deliverables
Firmware Development |  | Target Weight ≤ 2.5 grams
Schematic Drawing |  | Max Board Size (17.5 mm × 30 mm)
PCB Layout |  | Powered by LiPo battery, 3.7 V
Gerber Files |  | USB-C connector
Bill of Materials (BOM) |  | Software | Design
PCB Fabrication Ordering |  | Arduino IDE Compatable | User interface
PCB Assembly (soldering components) |  | EEPROM Data Storage | Data processing
Board Testing |  | Bluetooth For Data Transfer. | Communication protocols
3D Enclosure Design |  |  | Error handling
5. Unallocated Task Time Tracking
Task Description |  |  |  |  | Hours Spent
|  | Hours: |  |  | 0
6. Additional Expenses :
Item / Description | Category | Notes | Cost per Unit (€) | Units | Total (€)
PCB Fabrication (JLCPCB) | Fabrication |  |  |  | 0
Customs VAT | Customs/Tax |  |  |  | 0
Enclosure Printing | Outsourcing |  |  |  | 0
PCB Assembly | Assembly Service |  |  |  | 0
Components | Components LCSC |  |  |  | 0
Unit Testing Labor | Testing |  |  |  | 0
Delivery to Client | Logistics |  |  |  | 0
Others |  |  |  |  | 0
|  |  |  | Total Cost: | 0
7. Payment Section
Hourly Payments
Task / Milestone | Rate (€/hr) | Hours Worked | Amount (€) | Paid (€) | Remaining (€)
Milestone 1 | 15 | 16 | 240 | 171 | 69
Milestone 2 | 15 | 54 | 810 | 429 | 381
Milestone 3 | 15 | 16 | 240 | 429 | -189
Extra Tasks (Unallocated) | 15 | 0 | 0 |  | 0
Additional Expenses | Nil | Nil | 0 |  | 0
Total Amount: |  | 86 | 1290 | 1029 | 261
Thank you for choosing to work with me. I truly appreciate your trust, and I’ll do my best to bring your idea to life with precision, dedication, and transparency. This spreadsheet has been created to provide a clear overview of project scope, progress, and costs, ensuring full visibility at every step. Please Note: The quotation provided does not include external expenses such as: - Component sourcing (AliExpress, Digi-Key, etc.) - PCB fabrication or assembly services (e.g., JLCPCB, PCBWay) - Import duties, VAT, or customs clearance fees - Packaging or shipping of prototypes - Specialized tooling or any outsourced service costs - These costs will be discussed and billed separately if required during the project. Looking forward to building something great together from concept to completion, I'm here as your technical partner. Warm regards, M. Zaeem Electronics & Embedded Systems Engineer
Project Requirements The project involves designing and building a miniature, altimeter for model rockets. The device must record altitude and optional acceleration in non-volatile memory and allow post-flight data download to a laptop. The system should use Arduino-compatible components and software, with the option for wireless data transfer. The final design will include a lightweight custom PCB fitting within a 17.5 mm × 30 mm cylinder.
Core Requirements:
Microcontroller: nRF52840, Arduino-compatible.
Sensors: Pressure sensor: BMP390, Accelerometer: BMA253 or BMI270 (optional 3- or 6-axis)
Memory: EEPROM for non-volatile storage.
Connectivity: USB-C; optional Bluetooth for data transfer.
Power: Connector for single-cell LiPo battery.
Data Handling: Store flight data in EEPROM and provide access for download to a laptop. Optionally send data via Bluetooth or Arduino Cloud.
PCB Design: Schematic and layout in KiCAD or similar; target mass ≤ 2.5 grams.
Software Platform: Arduino IDE; optional Python/Processing for data analysis.
Hardware Sourcing: Use readily available, reliable components.
Developer Expertise Required: Firmware development, microcontrollers, programming.

## Component List
Sr. No | Component Name | Variant | Description / Use | Link to Cart | Quantity | Unit Price | Total Price (Euro)
1 | LSM6DSO32 6-DOF Accelerometer Adafruit | 1528-4692-ND | Measures acceleration and rotation. | https://www.digikey.fi/short/0h7tf7fn | 1 | 10.65 | 10.65
2 | nRF52840 Module with Antenna | 672-NINA-B306-01BCT-ND | Bluetooth wireless module for for prototyping. | https://www.digikey.fi/short/0h7tf7fn | 1 | 6.93 | 6.93
3 | BMP390 Precision Barometric Sensor Adafruit | 1528-4816-ND | Measures altitude via pressure. | https://www.digikey.fi/short/0h7tf7fn | 1 | 9.33 | 9.33
4 | Nano 33 BLE Rev2 Arduino | 1050-ABX00071-ND | Microcontroller for prototyping. | https://www.digikey.fi/short/0h7tf7fn | 1 | 19.69 | 19.69
5 | Seeed Studio XIAO ESP32C3 | 1597-113991054-ND | Backup Option Microcontroller for prototyping. | https://www.digikey.fi/short/0h7tf7fn | 1 | 4.25 | 4.25
|  |  | Aproximate Bill of Materials = |  |  |  | 50.85
Not shipped is red
Shipped is yellow
Arrived is green
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28

## Additional Project Information
Additional Project Information
2
Hi Chris,
Thank you for your patience. I’ve completed the component evaluation for your altimeter project and finalized the hardware approach.
We have two options for the microcontroller:
Bare nRF52840 IC – This requires designing a full RF section (antenna, matching network, etc.) and obtaining CE/FCC certification, which adds complexity, cost, and time.
u-blox NINA-B306-01B Module – This module integrates the same nRF52840 chip, includes an onboard antenna, and is already CE and FCC certified. It’s compact (approximately 10 mm x 15 mm), making it ideal for the rocket’s limited payload diameter (<17.5 mm).
After analysis, I’ve selected the u-blox NINA-B306-01B as the best option for this project due to its reliability, certification compliance, and size efficiency.
For the sensors:
Pressure Sensor: BMP390 (Adafruit Precision Barometric Sensor)
Accelerometer/Gyroscope: LSM6DSO32 (Adafruit 6-DOF IMU) — chosen over BMA253/BMI270 due to availability and superior stability.
For early firmware development and testing, I’ll use the Arduino Nano 33 BLE Rev2, which uses the same nRF52840 core. This will let us prototype the firmware and data logging functions before finalizing the custom PCB.
I’ve prepared a separate component list with all required sensors and parts, including purchase links. Please place the order as soon as possible so the components arrive on time and we can ensure smooth progress before the project deadline. Once they arrive, I’ll start firmware testing and sensor integration right away.